## Instructions
📋 Change Order Template — Instructions
BuiltRight Academy ¦ builtrighthq.com
— Always document scope changes in writing before doing the work. —
© 2026 BuiltRight Academy ¦ builtrighthq.com

## Change Order
CHANGE ORDER
[YOUR COMPANY NAME] |  | CO #: | CO-001
|  | Date: | 03/10/2026
Original Contract: | PROP-2026-018
Original Amount: | 10315
Client: | Robert & Maria Garcia
REASON FOR CHANGE
During demo, discovered water damage behind shower wall requiring additional repair before tile installation. Client also requested upgrade from standard to heated tile floor.
CHANGES
Description | Type | Hours/Qty | Amount
Replace rotted studs (3) and subfloor section | Add | 1 | 450
Mold remediation — treat & seal affected area | Add | 1 | 350
Heated floor mat — Nuheat 35 sq ft + thermostat | Add | 1 | 680
Heated floor installation labor | Add | 4 | 280
Standard tile installation labor (reduced — partial overlap) | Remove | 1 | -120
Net Change:
New Total:
Timeline Impact: Adds approximately 2 additional work days.
AUTHORIZATION
Client Signature: _______________________ Date: ____________
Contractor Signature: ____________________ Date: ____________