## Instructions
📋 Professional Proposal — Instructions
BuiltRight Academy ¦ builtrighthq.com
— HOW TO USE —
1. Replace all bracketed text. 2. Customize scope for your project.
3. Update pricing. 4. Print or PDF and present to client.
© 2026 BuiltRight Academy ¦ builtrighthq.com

## Proposal
PROJECT PROPOSAL
[YOUR COMPANY NAME] |  | Proposal #: | PROP-2026-018
[Address] ¦ [Phone] ¦ [Email] ¦ [Website] |  | Date: | 03/10/2026
License #: [Number] ¦ Insured ¦ Bonded |  | Valid Until: | 04/09/2026
PREPARED FOR: |  | PROJECT:
Robert & Maria Garcia |  | Master Bathroom
789 Maple Drive, Austin, TX 78704 |  | Complete Renovation
(512) 555-8901 ¦ garcia.home@email.com
SCOPE OF WORK
1. Complete demolition of existing bathroom including tile, fixtures, vanity, and drywall as needed.
2. Plumbing: Relocate shower valve, install new supply lines, replace drain assembly.
3. Electrical: Install new exhaust fan (110 CFM), add 2 GFCI outlets, upgrade lighting circuit.
4. Waterproofing: Install Schluter Kerdi membrane in shower area (walls and floor).
5. Tile: Install 12x24 porcelain tile on floor and shower walls (approx. 85 sq ft total).
6. Install 60" double-sink vanity with quartz countertop and undermount sinks.
7. Install new toilet (Toto Drake II elongated, ADA height).
8. Paint all walls and ceiling — 2 coats Benjamin Moore Regal (color TBD by client).
9. Install all trim, hardware, accessories (towel bars, toilet paper holder, mirror).
10. Final cleanup, debris removal, and walk-through inspection.
PROJECT TIMELINE
Phase | Description | Duration
Week 1 | Demolition, rough plumbing & electrical | 5 business days
Week 2 | Waterproofing, tile installation | 5 business days
Week 3 | Vanity, countertop, fixtures, paint | 5 business days
Week 4 | Trim, hardware, final inspection, punch list | 5 business days
INVESTMENT
Materials & fixtures |  |  | 4890
Labor |  |  | 5100
Permits & inspections |  |  | 325
PROJECT TOTAL
PAYMENT SCHEDULE
Deposit (50%) |  | Due upon acceptance
Progress (25%) |  | Due at tile completion
Final (25%) |  | Due upon final walk-through
ACCEPTANCE & AUTHORIZATION
By signing below, I/we accept this proposal, agree to the terms above, and authorize [YOUR COMPANY NAME] to begin work upon receipt of the deposit.
Client Signature: _________________________________ |  | Date: _______________
Printed Name: ___________________________________
Contractor Signature: _____________________________ |  | Date: _______________