## Instructions
📋 Job Costing Tracker — Instructions
BuiltRight Academy ¦ builtrighthq.com
— HOW TO USE THIS TEMPLATE —
1. Update job info at the top (name, client, dates).
2. Replace example line items with your actual job costs.
3. Enter estimated costs BEFORE the job starts.
4. Update actual costs AS expenses come in.
5. Variance and Status columns update automatically.
6. Enter your contract price in Profit Analysis to see net profit.
— WHY JOB COSTING MATTERS —
• Most contractors think they make money on every job. They don't.
• Job costing reveals which job TYPES are profitable and which aren't.
• Track every job for 3 months — you'll find at least one service you're losing money on.
• Use this data to adjust pricing on your next estimate.
© 2026 BuiltRight Academy ¦ builtrighthq.com

## Job Costing
JOB COSTING TRACKER
Job Name: | Miller Kitchen & Bath Remodel |  | Estimated Total:
Client: | David & Lisa Miller |  | Actual Total:
Start Date: | 02/15/2026 |  | Profit/Loss:
Category | Description | Estimated | Actual | Variance | Status
Materials | Cabinets — 12 LF uppers + lowers | 4200 | 4350
Materials | Countertops — Quartz 60" | 3200 | 3200
Materials | Tile — Porcelain floor + backsplash | 680 | 720
Materials | Plumbing fixtures — Sink, faucet, disposal | 850 | 890
Materials | Electrical supplies — Wire, outlets, switches | 340 | 310
Materials | Paint — 4 gal interior + primer | 280 | 295
Materials | Hardware — Pulls, knobs, hinges | 420 | 420
Materials | Miscellaneous — Adhesive, caulk, screws | 175 | 210
Labor | Demo crew — 2 workers × 8 hrs | 960 | 1040
Labor | Plumber — Rough-in + finish | 1700 | 1850
Labor | Electrician — Panel, outlets, lights | 960 | 960
Labor | Tile installer — Floor + backsplash | 1800 | 2100
Labor | Painter — Walls, ceiling, trim | 640 | 640
Labor | Finish carpenter — Trim, hardware | 480 | 520
Equipment | Tile saw rental (1 week) | 150 | 150
Equipment | Dumpster rental (20 yd) | 375 | 375
Permits | Building permit — City of Springfield | 250 | 250
Permits | Electrical permit | 75 | 75
Subcontractors | HVAC — Relocate duct | 600 | 650
Subcontractors | Drywall repair | 400 | 400
Overhead | Insurance allocation | 320 | 320
Overhead | Vehicle/fuel | 180 | 200
Overhead | Office/admin time | 150 | 150
TOTALS
PROFIT ANALYSIS
Contract Price: | 22500
Total Costs:
NET PROFIT:
Profit Margin: